## Slide 1
Exchange Modernization Update
Progress, Resiliency & Capacity Outlook
May 2026

## Slide 2
Today's Agenda
1
Exchange Productivity Commentary - How are things going?
2
Exchange Resiliency - Progress on key initiatives
3
Capacity Forecast - When do we shift to more commercial?

## Slide 3
Productivity: Positive Trends
Chart: Stories Completed (Jan-Mar)
| January | February | March
Stories Completed | 207 | 271 | 386
Chart: Lead Time & Cycle Time Improvement
| January | February | March
Lead Time (days) | 30 | 33 | 8
Cycle Time (days) | 44 | 44 | 23

## Slide 4
Beyond the Metrics: Foundation Building
Organizational Changes
New team topology aligned to future decoupled architecture ✓
Implementing "Reverse Conway Maneuver" for autonomous teams ✓
Talent Upgrade & Hiring
Hands-on Engineering Leadership upgrade
  1 Director → 4 Directors ✓
  3 EMs → 12 EMs (in progress)
Key IC roles being filled to enable independent delivery (in progress)

## Slide 5
Exchange Resiliency Update
Priority | Status | Notes
DB Migration to managed databases | On Track | Atlas Migration completion Aug 19
Disaster Recovery (4h RTO, 2h RPO) | On Track | Lower env test: RTO 7h, RPO 0:15h. Internal Oct, External Dec
All vulnerabilities within SLA / Eliminate EOL | Mixed | Red Mythos July 4 at risk, tracking end of July finish
Industry Continuity Solution | On Track | Building GHXi FTE team
Increase Modularity (Break the Monolith) | In Progress | "Good enough" stage by end of Q4

## Slide 6
The Constraint: Breaking the Monolith
Improvements will be incremental until we achieve Autonomous Teams
What does "Autonomous Teams" mean?
Teams that can deploy independently, on demand, without coordinating with other teams - as long as no APIs, contracts, or data models are changed.

## Slide 7
Autonomous Teams - Phase 1 Definition of Done
Target: End of Q4 2026
1. Org Change ✓
New team topology aligned to future decoupled architecture
2. Teams Correctly Staffed & Skilled (In Progress)
Dedicated Engineering Manager
Dedicated Product Owner
Key roles filled
Cross-functional upskilling in addition to development (CI/CD, Infra, Security, QE)
3. Clear Ownership (In Progress)
100% clear what each team owns (mutually exclusive, collectively exhaustive)
4. Independent Deployment (In Progress in some teams)
Code decoupled into standalone repos (or modular monolith)
Teams own and operate deployment pipelines
Minimal coordination required for local deployments

## Slide 8
Technical Work before Capacity Shift
MUST DO (Cannot shift capacity until done)
P0 Data layer improvements:
Address stability & scalability limitations
Move to cloud-native, infinitely scalable storage (DynamoDB, S3) where appropriate
Redo data modelling according to read/write patterns
Thoughtful data retention policies
Benefits:
Stability / Scalability
Cost reduction
REQUIRED BUT NEGOTIABLE (Timing flexible)
Still urgent, but trade-offs possible:
Event/Messaging system (replace Mongo-based Event Bus)
Infinitely scalable queue processors/event subscribers
Cloud-native infra (containers, managed services vs EC2)
Enhanced observability & instrumentation
Notes:
Veritas/Kickdrum will likely comment on these gaps
Still urgent, but timing and sequencing become a more “normal” discussion of tradeoffs between commercial / technical initiatives (ROI vs. risk vs. scalability etc.)

## Slide 9
Timeline & Capacity Evolution
Q1 2026
Q2 2026
Q3 2026
Q4 2026
Q1 2027
Q2 2027
Q3 2027
MongoDB → Atlas
Disaster Recovery
Red Mythos (Vuln/EOL)
Autonomous Teams / Break Monolith
P0 Database Improvements
Other (Messaging, Cloud-Native Infra, …)
Capacity (Com/Tech)
25/75
25/75
25/75
25/75
50/50
50/50
70/30
Timeline Confidence:
High
Medium

## Slide 10
Timeline & Capacity Evolution
Q1 2026
Q2 2026
Q3 2026
Q4 2026
Q1 2027
Q2 2027
Q3 2027
MongoDB → Atlas
Disaster Recovery
Red Mythos (Vuln/EOL)
Autonomous Teams / Break Monolith
P0 Database Improvements
Other (Messaging, Cloud-Native Infra)
Capacity (Com/Tech)
25/75
25/75
25/75
25/75
50/50
50/50
70/30