## Slide 1
Risks & Mitigations
Table: Risks and Mitigations
Initiative | Risks | Mitigations
MongoDB to Atlas | Minimal Risk at this point | No mitigation needed at this point
Disaster Recovery | Unknown Unknowns, Outside dependencies on Exchange | Discovery work started, lower env dry runs, targeting Oct vs Dec for buffer, engaging teams outside Exchange
Red Mythos | High coupling → high complexity → big bang approach, large version jumps | Sequestered team on dedicated branch/env, heavy AI use for remediation and testing, all hands plan for merging
Autonomous Teams / Break Monolith | Impact from Atlas, DR, Red Mythos; Hiring (esp. India); High coupling; Unknown unknowns | Fast-tracking DR and Red Mythos, India comp flexibility, giving teams flexibility on reaching independent deployments
COMMON RISK | Competing priorities & interference on same monolithic codebase | Laser focus Q3-Q4 (see next slide)

## Slide 2
Q3 - Q4 Technical Laser Focus
Strict direction to teams for Q3 and Q4:
75% Technical Capacity - Three Buckets Only:
Red Mythos (Vulnerabilities & EOL Technologies)
Disaster Recovery
Autonomous Teams / Breaking the Monolith