## Slide 1
Today's Agenda
Commentary / State of the Union on Productivity Improvements
Update on Exchange Resiliency Work
Capacity Planning Forecast

## Slide 2
Executive Summary
PRODUCTIVITY
Measurable improvement, structural ceiling remains
Stories completed up 86% (207→386)
Cycle time down 48% (44→23 days)
Gains are incremental until monolith + org structure changes complete
RESILIENCY - "WHEN ARE WE DONE?"
2 Must-Do
12 autonomous teams deploying independently (70% org work done)
Data layer modernization (MongoDB → purpose-built stores)
CAPACITY FORECAST
Shift from reactive to strategic
Q2: 60% firefighting / 40% strategic
Q4: 30% firefighting / 70% strategic

## Slide 3
Productivity - The Data
4-Month Trends (Jan → Mar)
Stories Completed
207 → 271 → 386 (+86%)
Lead Time to Change
30 → 33 → 8 days (-73%)
Cycle Time
44 → 44 → 23 days (-48%)
Also:
Last 3 releases clean (no major incidents)
AI library launched (Claude Code adoption growing)
Exchange Health Score beta (leading indicator dashboard)
Chart: Productivity Trends
Chart: Productivity Trends (Jan - Mar 2026)
| Jan | Feb | Mar
Stories Completed | 207 | 271 | 386

## Slide 4
Productivity - Challenges
TECHNICAL & ORGANIZATIONAL
The monolith (testing/risk/blast radius bottleneck)
The org was also "monolithic" (1 director, 80 people) — we're solving this
Culture debt (fear of releasing, "everything is a project")
PROCESS & VISIBILITY
Visibility/reporting problem (roadmaps at epic level, always a new data request)
Competing priorities, "show your progress" asks
Product-Engineering engagement (best practice: 1-1 PO to EM, we don't have that)
Large opportunity cost at leadership level (hands-on leadership required through change)

## Slide 5
Productivity - In Summary
We are making incremental productivity improvements.
As long as we operate in a monolithic codebase, deployment footprint, and team structure, improvements will be incremental rather than transformational.
The org transformation (1 director → 4 directors, 12 EMs) is the foundation for exponential gains.

## Slide 6
Other Resiliency Priorities - Scorecard
Table: Resiliency Status
Priority | Status | Notes
DB Migration to Managed Databases | 🟢 On track | Atlas Migration completion Aug 29
DR Test (RTO/RPO) | 🟢 On track | Lower environment test: RTO 4:45, RPO 0:15. Internal target October, External comms December
Red Mythos/Vulnerabilities | 🟡 Complex | Monolith dependencies - targeting July 2 completion
EOL Technologies | 🟡 Complex | Atlas, Elasticsearch, Java upgrades, OSS upgrades
ICS (Industry Continuity) | 🟢 On track | Building FTE team to own this
Breaking the Monolith | 🟡 In progress | The big one (next slides)

## Slide 7
The Monolith
Reference: Building Autonomous Teams Deck (Slide 4)
Visual showing the vicious cycle:
Large codebase → High risk → Defensive testing → Slow releases → Batching → Larger changes → Higher risk

## Slide 8
The Cost of the Monolith
COST FOR PRODUCT & CUSTOMERS
Innovation throttled (everything is a "project")
Poor deployment frequency
Long lead time for changes
Cannot respond quickly to customer needs
Slow incident remediation
Delayed security fixes
COST FOR ENGINEERING
Things that should be easy are now high risk and difficult
Uncertainty of impact / side effects
Coordination overhead
Lack of autonomy
Difficult to prioritize and manage mixed work streams

## Slide 9
Monolith vs. Services Owned by Autonomous Teams
Reference: Building Autonomous Teams Deck (Slide 9)
Visual comparing:
Monolith (one big deployment) vs. Services (independent deployments)
Shows the target state with clear ownership and independent deployment

## Slide 10
What Does Autonomous Teams Mean?
It is team structure, process, AND architectural
Team Structure & Process:
Dedicated EM and Product Owner (1:1 ratio)
6-8 engineers (cross-functional: backend, frontend, QA, DevOps)
Sprint independently (dedicated Jira project, backlog)
"Team API" (Slack channels per convention, clear interfaces)
Architectural:
Own and deploy their component independently (no monolith coordination)
Own their application-near infrastructure
Own their deployment pipelines
Services, not monolith modules
This is how it ties back to "Increase Modularity" priority (breaking the monolith)

## Slide 11
"When Are We Out of the Woods?"
Must Haves (We won't be stable without these)
1. 12 Autonomous Teams Operating Independently
Dedicated EM, PO (1:1 ratio)
Own and deploy components independently
Own application-near infrastructure
Own deployment pipelines
Sprint independently
✅ Progress: 70% (org structure in place, technical decoupling starting)
2. Data Stored in Purpose-Built Products
MongoDB → RDS, DynamoDB, Aurora, S3 (right tool for job)
Scalability becomes elastic (not manual intervention)
HA/DR becomes config setting (not a project)
Cost optimization unlocked
🟡 Progress: 20% (Atlas migrations in progress, architectural changes in planning)

## Slide 12
We Will Still Have a Backlog
Still required, but timing negotiable. Veritas/Kickdrum will likely comment.
PLATFORM & DATA
Event/messaging system replacement (EventBus MongoDB → SQS/Kafka)
Activity Flow optimization (S3-based storage vs 188M docs/day churn)
Observability improvements (extend log retention, proactive alerting)
Service health checks
DEVELOPMENT & DELIVERY
Testing framework modernization (replace Tandoori)
Feature flags system
Mapping tool modernization (EDI → JSON)
Cloud-native infra (serverless, managed services)

## Slide 13
Capacity Evolution (Q2 → Q3 → Q4)
Key: Autonomous teams reduce KTO burden, unlock roadmap capacity
Chart: Capacity Allocation
Chart: Q2 2026 (Baseline)
| Technical Work (70%) | Commercial Roadmap (30%)
Q2 2026 (Baseline) | 70 | 30
Chart: Q3 2026 (Transition)
| Technical Work (60%) | Commercial Roadmap (40%)
Q3 2026 (Transition) | 60 | 40
Chart: Q4 2026 (Stabilized)
| Technical Work (50%) | Commercial Roadmap (50%)
Q4 2026 (Stabilized) | 50 | 50