## Slide 1: Exchange Resiliency Update
Promised vs. Completed Work Analysis | June 26, 2026 | Marten Engblom for CJ Singh

## Slide 2: Agenda
01 Executive Summary & Overall Progress
02 Database & Data Layer
03 Architectural Decoupling
04 Infrastructure & Resilience
05 Observability & Operations
06 Process, Governance & Security
07 Key Metrics & Impact
08 Analysis & Strategic Implications
09 Next Steps & Recommendations
Exchange Resiliency · June 2026

## Slide 3: Executive Summary
43% of promised work completed and deployed to production
30% actively in progress — sustained momentum across all dimensions
27% status unclear — candidates for director input sessions
54 distinct initiatives tracked across 5 resiliency dimensions
Strongest performance: Observability & Operations — 75% complete
Most active: Database & Data Layer, Infrastructure & Resilience
Status: ✅ Completed | 🔄 In Progress | ❓ Unknown
18 months of delivery across 5 resiliency dimensions

## Slide 4: Overall Progress Across All Dimensions
Group ✅ Done 🔄 Active ❓ Unknown Total
─────────────────────────────────────────────────────────────
Database & Data Layer 5 4 3 12
Architectural Decoupling 3 4 6 13
Infrastructure & Resilience 4 5 2 11
Observability & Operations 6 0 2 8
Process, Governance & Security 5 3 2 10
─────────────────────────────────────────────────────────────
TOTAL 23 16 15 54
Observability 75% · Process/Gov 50% · Database 42% · Infrastructure 36% · Architecture 23%

## Slide 5: Database & Data Layer
Dimension 01 of 05

## Slide 6: Database & Data Layer
✅ IBR User Data Separation Ph.2 & 3 — 4 tables (~40% TPM footprint) moved to dedicated BR DB
✅ BR User Data Cache Replacement — 80% reduction in TPM database reads (Aug 2025)
✅ TPM Migration to Aurora — Multi-region sync for DR/failover (May 2026–present)
✅ Semijoin Optimization — MySQL 8.0 incident fallout remediated (Jul 2025)
✅ MEX Query Optimization — Prevent incidents from slow/bad queries (Jun 2026)
✅ Move D Semaphore to Redis — Removes AuditDB/D Semaphore dependency (Feb 2026)
✅ Data Retention — Cost savings + efficiency (Apr 2025)
🔄 Atlas Migration — MongoDB → managed Atlas (ongoing)
🔄 Elasticsearch → Elastic Cloud managed service (ongoing)
🔄 IBR Data Migration | 🔄 Replace direct DB calls with MEX APIs
❓ ES depressurization | ❓ Registration query fixes | ❓ MyExchange query fixes

## Slide 7: Architectural Decoupling
Dimension 02 of 05

## Slide 8: Architectural Decoupling
✅ SSO: Identity Service DB out of Audit Server — AuditDB degradation no longer impacts logins (Aug 2025)
✅ SSO: TPM Database Separation Ph.1 — 52 tables migrated TPM DB → dedicated SSO DB (Nov 2025)
✅ Dedicated API Gateway for Org API — External teams no longer forced to failover with Exchange (May 2026)
✅ Tracking Engine Decoupling — Separate repo, dedicated Bamboo pipeline
✅ Notifications Engine Decoupling — Separate repo, dedicated Bamboo pipeline
✅ Visibility UIs Decoupled — Notifications, Transactions, Orders, Invoicing out of monolith
✅ AdapterAPI Part 2 — IO adapters decoupled from TPM
🔄 RC 2.0 Monolith Decoupling — API on GitHub; UI work not yet started (Feb 2026–present)
🔄 Monolith Decoupling Spike Epic — Services mapped for migration planning (Jun 2026–present)
🔄 User Data / IBR Decoupling (ongoing)
❓ Hash Map LB | ❓ Dead Listener Refactor | ❓ Feed Processor Refactor | ❓ Data Poller overhaul

## Slide 9: Infrastructure & Resilience
Dimension 03 of 05

## Slide 10: Infrastructure & Resilience
✅ Performance Environment — Jan–Jun 2025; used for Atlas, Elastic Cloud, Aurora upgrade testing
✅ EventBus Resiliency — Doc processing less impacted during incidents (Jul 2025)
✅ Processing Engine Robustness — Threadpool tuning, tracking priorities, Java Flight Recorder (Apr 2025)
✅ IO Guarantee — SQS Backup for Native Comms; improved reliability for critical flows
✅ Industry Continuity Solution (ICS) — Deployed and active
🔄 Disaster Recovery — DR drills, RTO 4hrs / RPO 2hrs targets, runbooks (ongoing)
🔄 Tracking Resiliency Ph.1 & 2 — Bugs + race conditions (Ph.3 pending)
🔄 MongoDB to Atlas | 🔄 Elasticsearch to Elastic Cloud | 🔄 TPM to Aurora
❓ Universal Scheduler Migration | ❓ Event Bus Next Generation

## Slide 11: Observability & Operations
Dimension 04 of 05 · 75% Complete

## Slide 12: Observability & Operations
✅ Heartbeat: CoreX BI — CoreX BI, ABL, ILM, SQS/DQS metrics, DP Backlog visibility (Mar–Sep 2025)
✅ Heartbeat: Configuration Cache — Reduced DynamoDB reads; lower costs + faster API response (Sep 2025)
✅ Org API Automated Validation — Validation: multiple person-days → 2 minutes (May 2026)
✅ Canary Program — Kinesis stream of Event Bus events; predictive monitoring deployed
✅ CoreX BI Dashboard — Bulk Load tracking, document throughput, Heartbeat visibility
✅ Feature Flagging — Safer incremental rollouts enabled
✅ Incident Management Process Improvements — Mature escalation paths + executive comms protocols
✅ Alerting & Monitoring — Gaps addressed across stack
❓ DB spike detection and alerting | ❓ SLA monitoring and rebate tracking

## Slide 13: Process, Governance & Security
Dimension 05 of 05

## Slide 14: Process, Governance & Security
✅ Mongo/Spring Library Upgrades — Mongo 8.X support, EOL libs remediated, vulnerability fixes (Aug 2025)
✅ SSO: SAML Adapter — SAML protocol added to GHX SSO (Jan 2026)
✅ SSO: Liquibase Execution Fix — Moved out of EC2 startup; eliminated release failures (Nov 2025)
✅ Release Rigor & Change Management — Multi-person go-live audit + CoreX permission audit
✅ Customer Empathy Training — Team-wide rollout completed
🔄 Red Mythos Exchange — Vulnerabilities within SLA, EOL elimination (Aaron ownership)
🔄 All vulnerabilities within SLA (ongoing) | 🔄 Eliminate EOL technologies
❓ Testing Maturity improvements | ❓ Customer communication strategy

## Slide 15: Key Metrics & Impact
PERFORMANCE GAINS
· 80% reduction in TPM database reads (BR User Data Cache)
· 30 min → 5 min bulk load time (Org Search in Elasticsearch)
· Multiple person-days → 2 minutes validation (Org API GitHub automation)
ARCHITECTURAL PROGRESS
· 52 tables migrated: TPM DB → dedicated SSO DB
· 4 tables migrated: TPM DB → dedicated BR DB (~40% of TPM footprint)
· 4 UIs fully decoupled from monolithic ALL repo
RELIABILITY & SECURITY
· Multi-region data sync enabled (Aurora migration)
· Performance environment preventing production incidents
· Mongo 8.X support, EOL remediated, SAML protocol added to SSO
Quantifiable outcomes — 18 months of delivery

## Slide 16: What This Data Tells Us
COMPREHENSIVE EXECUTION
Progress across all 5 dimensions — not cherry-picking easy wins.
OPERATIONAL EXCELLENCE
75% in Observability & Operations. Mature monitoring, alerting, incident management now in place.
THIS WEEK VALIDATES STRATEGY
June 22–24: monolithic coupling caused 6 simultaneous issues. Every root cause addressed by ongoing work.
MOMENTUM SUSTAINED
30% actively in progress. Atlas, ES, Aurora migrations all moving simultaneously.
ARCHITECTURAL TRANSFORMATION
Only 23% in Decoupling — expected given complexity. 4 major initiatives in flight.
INFRASTRUCTURE READY
Performance env, monitoring, incident processes mature. Foundation for next phase is set.
DOCUMENTATION NEEDED
27% unclear — likely done but undocumented. Director input sessions recommended.
CONWAY'S LAW OPPORTUNITY
4 directors, 12 managers, small teams. Aligning team to service boundaries accelerates decoupling.
NEXT PHASE
Baselines needed: incident freq, MTTR, deploy freq, change failure rate, team autonomy scores.

## Slide 17: Strategic Implications
June 22–24 Incident — Why This Work Matters
· Monolithic coupling caused 6 simultaneous issues
· Deployment pipeline fragility prevented rapid fixes
· Every root cause addressed by autonomous teams + continued decoupling
Conway's Law — Structure Must Follow Architecture
· Org structure (4 directors, 12 managers, small teams) is in place
· Aligning team to service boundaries accelerates decoupling organically
Infrastructure Foundation Is Ready
· Performance environment, monitoring, incident management: mature
· Confidence in production deployments significantly improved

## Slide 18: Next Steps & Recommendations
THIS WEEK (Done)
✅ Completed items extracted from resiliency doc
✅ All sections populated with Jira tickets & metrics
NEXT 2 WEEKS
· Review with directors (Daniel, Aaron, Arshad, Ramesh)
· Confirm 15 Unknown items
· Aaron: Red Mythos status + metrics
· All: customer empathy training dates, audit metrics
Q3 2026
· Establish transformation success baselines:
— Incident frequency + MTTR
— Deployment frequency + change failure rate
— Team autonomy + cross-team dependency counts
· Milestones docs for Atlas, ES, Aurora, DR drills
Q4 2026+
· Monthly report updates · Quarterly leadership reviews
· Broader transformation story: internal + external
Immediate · Q3 · Q4

## Slide 19: Thank You
Marten Engblom
mengblom@ghx.com
Prepared for: CJ Singh
Report Date: June 26, 2026 | Next Review: July 10, 2026

## Slide 20
Exchange Resiliency Update
June 2026