## Slide 1: Exchange Resiliency Report
Exchange Resiliency Report
Promised vs. Completed Work Analysis
June 26, 2026

## Slide 2: Agenda
Executive Summary — Key findings and progress overview
Status Summary — Progress across 5 resiliency dimensions
Completion Rates — Visual comparison by dimension
Detailed Progress — All 5 dimensions reviewed
Impact & Insights — Quantifiable improvements delivered
Strategic Implications — What the June incident tells us
Path Forward — Immediate and short-term actions

## Slide 3: Executive Summary
Status Legend:
  ✅ Completed — Work is done and deployed
  🔄 In Progress — Work actively underway or partially complete
  ❓ Unknown — Status unclear from documentation
Key Findings:
  43% of promised work completed (23 of 54 items)
  30% actively in progress (16 items)
  27% status unclear (15 items)

## Slide 4: Overall Progress Across All Groups
Group | ✅ Completed | 🔄 In Progress | ❓ Unknown | Total Items
Database & Data Layer | 5 | 4 | 3 | 12
Architectural Decoupling | 3 | 4 | 6 | 13
Infrastructure & Resilience | 4 | 5 | 2 | 11
Observability & Operations | 6 | 0 | 2 | 8
Process, Governance & Security | 5 | 3 | 2 | 10
TOTAL | 23 | 16 | 15 | 54

## Slide 5: Completion Rate by Dimension
Observability & Operations
75%
6 of 8
Process, Governance & Security
50%
5 of 10
Database & Data Layer
42%
5 of 12
Infrastructure & Resilience
36%
4 of 11
Architectural Decoupling
23%
3 of 13
Key Insight: Observability infrastructure is mature and comprehensive, while architectural decoupling shows expected lower completion given the complexity and scope of monolith transformation.

## Slide 6: Detailed Progress

## Slide 7: Database & Data Layer
What We Promised
  ✅ Audit DB optimization
  🔄 MongoDB to Atlas migration
  🔄 Elasticsearch to Elastic Cloud
  ✅ TPM database optimization
  ✅ Database syncing & cleanup
  🔄 IBR data migration
  🔄 Replace direct DB calls with APIs
  ❓ ES depressurization
What We Completed
  IBR User Data Separation (40% of TPM footprint)
  BR User Data Cache (80% DB read reduction)
  TPM to Aurora migration (multi-region sync)
  Semijoin optimization restored
  MEX query optimization
  D Semaphore moved to Redis
  Data retention improvements
  30min → 5min bulk load time (Org Search in ES)

## Slide 8: Architectural Decoupling
What We Promised
  ✅ SSO Decoupling
  🔄 User Data Decouple
  ✅ Tracking Engine Decouple
  🔄 IBR Decoupling
  🔄 Document Processing Phase 2
  ❓ Hash Map Load Balancing
  ❓ Dead Listener Refactor
What We Completed
  SSO: 52 tables migrated from TPM DB
  SSO: AuditDB separation complete
  4 UIs decoupled from monolithic repo
  Tracking & Notifications engines separated
  Dedicated API Gateway for Org API
  RC 2.0 monolith decoupling underway
  AdapterAPI Part 2 completed

## Slide 9: Infrastructure & Resilience
What We Promised
  🔄 Disaster Recovery
  ✅ Industry Continuity Solution (ICS)
  ✅ Performance Environment
  ✅ Performance Testing capability
  🔄 Managed Database Services
  ✅ Processing Engine enhancements
  ✅ IO Guarantee improvements
What We Completed
  Performance environment operational
  EventBus resiliency improvements
  Industry Continuity Solution deployed
  Tracking resiliency Phases 1 & 2
  IO Guarantee SQS backup
  Processing Engine threadpool tuning
  Java Flight Recorder for diagnostics

## Slide 10: Observability & Operations
What We Promised
  ✅ Alerting and Monitoring improvements
  ✅ Fix gaps in monitoring
  ✅ Visibility improvements
  ✅ Performance Testing framework
  ✅ Incident Management processes
  ✅ Feature Flagging capability
  ✅ Canary Program
What We Completed
  Heartbeat: CoreX Business Intelligence
  Heartbeat: Configuration Cache (reduced DynamoDB reads)
  Org API validation pipeline (2 minutes vs days)
  Canary Program deployed (document prediction)
  CoreX BI Dashboard operational
  Feature Flagging enabled for safe rollouts

## Slide 11: Process, Governance & Security
What We Promised
  ✅ Release rigor and change management
  🔄 All vulnerabilities addressed within SLA
  🔄 Eliminate EOL technologies
  ✅ Human Error Mitigation
  ✅ Customer empathy training
  ✅ Canary program communications
What We Completed
  Mongo 8.X support, EOL libs upgraded
  SAML protocol added to GHX SSO
  Liquibase execution moved to dedicated bamboo step
  Multi-person go-live audit implemented
  CoreX permission audit completed
  Customer empathy training rolled out

## Slide 12: Impact & Insights

## Slide 13: Key Metrics & Impact
80%
Reduction in
TPM DB Reads
83%
Bulk Load
Time Saved
99%+
Validation
Time Saved
Architectural Progress
• 52 tables migrated from TPM to dedicated SSO DB
• 4 tables migrated to dedicated BR DB (~40% of TPM footprint)
• 4 UIs fully decoupled from monolithic ALL repo
• Multi-region data synchronization enabled (Aurora)

## Slide 14: Strategic Implications
June 22-24 Incident Validates Strategy:
  Monolithic coupling caused 6 simultaneous issues
  Deployment pipeline fragility prevented rapid fixes
  Every root cause addressed by autonomous teams + continued decoupling
Infrastructure Foundation Ready:
  Performance environment, monitoring, and incident management processes are mature
  This foundation supports the next phase of architectural transformation

## Slide 15: Path Forward

## Slide 16: Next Steps
Immediate (This Week):
  Present findings to leadership
Short-Term (Next 2 Weeks):
  Review with directors to confirm status of 15 'Unknown' items
  Validate brainstormed list items and gather missing metrics
  Fill remaining gaps (Red Mythos status, audit results, training outcomes)
Medium-Term (Q3 2026):
  Establish baseline metrics for transformation success criteria
  Document ongoing migrations with completion timelines

## Slide 17
Marten Engblom
mengblom@ghx.com